## Savings Timetable
Savings - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Date of Meeting | Comments
S1 | Savings | Efficiency & Savings Board |  |  | 2024-03-12 | Share Budget Setting Timetable.
S2 | Savings | SLT - Savings and Efficiencies Challenge | Corporate Finance | Debbie Martin | 2024-05-10 | Briefing to SLT on the savings challenge (Include Non-Pay Savings Targets)
S3 | Savings | Templates to capture Savings distributed (High level and Detailed) - Organisation Change Business Cases | Corporate Finance | Annette Chan / Anna Hook | 2024-05-13 | Deadline for submission will be 2nd July for High level and 19th August for detailed (liaise with Strategic Change and Finance Business Partners if Business Case is required)
S4 | Savings | Templates to capture Savings distributed (High level and Detailed) - Non Pay | Corporate Finance | Annette Chan / Anna Hook | 2024-05-13
S5 | Savings | Submission deadline for high level savings templates | Force Commands | Chief Officers/Anna Hook | 2024-06-28 | Submit to Finance Business Partner (Strategic Change)
S6 | Savings | Efficiency & Savings Board | Strategic Change | Anna Hook | 2024-07-09 | Initial Strategic discussion on savings proposals received to date from commands (decisions required on which ones to progress)
S7 | Savings | Budget Holder Star Chambers for non pay savings | Corporate Finance / Force Commands |  | July & August | Individual sessions for budget holder and finance contact to discuss savings proposals
S8 | Savings | Submission deadline for savings templates | Force Commands | Chief Officers/Anna Hook | 2024-08-19 | Submit to Finance Business Partner (Strategic Change)
S9 | Savings | Commence QA of Savings Proposals | Strategic Change/Corporate Finance | Finance BP (Strategic Change)/Debbie Martin | 2024-08-20 | Quality Assurance of Savings Proposals
S10 | Savings | Corporate Finance Non Pay & Capital Star Chamber: 1 of 2. | Corporate Finance | BPs and MA s | 2024-09-03 | Review of current year forecasts to identify potential additional saving areas (ensuring no overlap with other savings proposals)
S11 | Savings | Corporate Finance Non Pay & Capital Star Chamber: 2 of 2. | Corporate Finance | BPs and MA s | 2024-09-05 | Review of current year forecasts to identify potential saving areas (ensuring no overlap with other savings proposals)
S12 | Savings | Efficiency & Savings Board | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook | 2024-09-12 | Overall savings proposals from commands prior to 7P Assessment agreed for inclusion in the next stage of the budget setting process.
S13 | Savings | Strategic Change commence 7 Pillar Assessment | Force Commands | Chief Officers/Anna Hook | 2024-09-13 | Work to commence after E&SB
S14 | Savings | Complete papers for Extraordinary Budget Setting SCCB (Inc. 7 Pillar Assessment) | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook | 2024-09-30 | 7 Pillar Assessment completed and returned to Corporate Finance for submission to Extraordinary Budget Setting SCCB
S15 | Savings | SCCB (Extraordiary Budget Setting) | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook | 2024-10-07 | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
From this point follow 'Strategic' timetable
2024-12-24
2025-01-03
2025-01-06
|  | Provision of Papers to PFCC CFO for the PF&CP Budget Working Group (4) |  |  | 2025-01-07
|  | Chief Constable sends final budget proposal letter and appendicies to PFCC |  |  | 2025-01-13
|  | Provision of Panel paper supporting papers to PFCC CFO (spreadsheets) |  |  | 2025-01-13
2025-01-13
2025-01-14
2025-01-22

## Investments Timetable
Investment - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Date of Meeting | Comments
IO1 | Investment - Other | Revenue Budget Bid Templates Issued (Basic Template) | Corporate Finance | Head of Financial Strategy | 2024-06-03 | Template issued to Finance Business Partners and Management Accountants. FBPs and MAs will liaise with Budget Holders to capture high level bids. Basic template. More detailed template issued once idea supported by Chief Officers.
IO2 | Investment - Other | Start engagement with Budget Holders to capture contractural & legal and service demand investment | Financial Performance and Reporting | BPs and MA s | 2024-06-03 | Finance Business Partners (FBPs) and Management Accountants (MAs)will work with budget holders where there are confirmed contractural, legal or service demand pressures. BPs and MAs responsible for submitting bid documentation that has been completed with input from subject matter experts within commands.
IO3 | Investment - Other | Deadline for submission of completed Basic Investment bid templates to Corporate Finance | Budget Holders | Budget Holders | 2024-07-12 | Bids to be collated by Corporate Finance and submitted for COG consideration.
IO4 | Investment - Other | High Level Investment bids to be considered by COG | COG | Chief Officers | 2024-07-24 | If bids supported, detailed template provided for submission by 30th August.
IO5 | Investment - Other | Deadline for submission of contractural, legal and service priority business cases. | Force Commands | BPs and MA s | 2024-08-30 | This will allow time for QA of bids prior to being forwarded for 7 Pillar Assessment
IO6 | Investment - Other | QA and review of detailed growth investment completed | Financial Performance and Reporting | BPs and MA s | 2024-09-09 | Finance Business Partners and Management Accountants provide detailed bids that have been signed off by Chief Officers to Head of Financial Strategy for consolidation. (Includes FMS identified strategic bids). At this point they are submitted to Strategic Change for 7 Pillar assessment.
IO7 | Investment - Other | 7 Pillar Assessment of Bids | Strategic Change | Anna Hook | 2024-10-03 | 7 Pillar Assessment completed and returned to Corporate Finance for submission to Extraordinary Budget Setting SCCB
IO8 | Investment - Other | SCCB (Extraordiary Budget Setting) | Corporate Finance | CFO / Head of Finance | 2024-10-07 | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
From this point follow 'Strategic' timetable

## Pay - Timetable
Pay Budget Setting - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Date
P1 | Pay | Officer, Staff & PCSO establishment extracted from HR system for pay budget setting (version 1) – as at 1st September 2024. | Financial Performance and Reporting | Head of Financial Performance and Reporting | 2024-09-02 | Corporate A/c Requested from HR. Corporate Accountant put into the pay budget model. RJ Team split up by commands (Dawn) and diseminate to BP team
P2 | Pay | Issue establishment version 1 to HR Advisors and Heads of Department / Commands. | Financial Performance and Reporting | Head of Financial Performance and Reporting | 2024-09-09 | wording of email agree with Richard/ Matt, Mas to make sure that any actions returned to HR are followed through.
P3 | Pay | Establishment version 1 returned by HR Advisors and Heads of Departments / Commands to CFO | Force | HR Advisors/Heads of Depts | 2024-09-20
P4 | Pay | Deadline for COG approved establishment changes to be sent to Organisational Management team to be included in pay budget setting. Any COG approvals after this date will require budget setting process approval | Financial Performance and Reporting | Head of Financial Performance and Reporting | 2024-10-04 | this is the last HR tracker.
P5 | Pay | CFO review of draft provisional pay budget setting information (1 of 2) | Financial Strategy | Head of Financial Strategy | 2024-10-08 | sit down with Matt and Sam to look at detailed timetable for work between 18th September and Oct 6.
P6 | Pay | CFO review of draft provisional pay budget setting information (2 of 2) | Financial Strategy | Head of Financial Strategy | 2024-10-22
P7 | Pay | Provisional Pay Budgets sent to CFO. | Financial Strategy | Head of Financial Strategy | 2024-10-25
From this point follow 'Strategic' timetable

## Capital Timetable
Capital - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Date | Comments
C1 | Capital | Engagement with Budget Holders commences to discuss existing and new Bugdet Setting Capital Investment bids | Corporate Accounting | Arfanara Naidu | 2024-06-03 | Early engagement with Budget Holders to discuss their capital needs.
C2 | Capital | Distribute Template to capture bids for new capital investment | Corporate Accounting | Arfanara Naidu | 2024-06-03 | The template will be the new business case template. This will be distributed earlier if available.
C3 | Capital | Estates Change Board | Corporate Finance | Force Commands | 2024-07-22 | Estates capital bids or significant increases to existing bids (more than 10% or £50k change)
C4 | Capital | DTOB | Corporate Finance | Force Commands | Jul/Aug (TBC) | Approval of IT Capital Bids or significant increases to existing bids to progress to SCCB
C5 | Capital | Deadline for updates to exisiting bids and new bids to be submitted to Corporate Accounting. (Other) | Force Commands |  | 2024-08-30 | Deadline is for 'other' Capital bids. Estates and IT will have other internal governance boards to accommodate which will require earlier deadlines if finance QA required beforehand
C6 | Capital | Send reviewed new capital bids to Strategic Change for 7 Pillar Assessment | Corporate Accounting | Arfanara Naidu | 2024-09-09
C7 | Capital | 7 Pillar Assessment of new Capital Bids | Strategic Change | Strategic Change | 2024-10-04 | Assessment completed and returned to Corporate Finance for submission to extraordinary SCCB
C8 | Capital | SCCB (Extraordinary Budget Setting) | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook | 2024-10-07 | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
From this point follow 'Strategic' timetable

## 21-22 Budget Timetable - Combin (hidden)
2021/22 Budget Setting - Detailed Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Deadline Date | Comments | Key Date

## Non Pay Star Chambers (hidden)
[5 empty] | y | Yes
List of sessions that each individual could attend |  |  |  |  | N | Cannot attend
| 4th September | 10th September | 17th September | Number of Codes | T | Tentative
Kate | n | y | y
Wendy | T | n | y
Dawn | y | y | y
Claira | y | y | y
Sam | y | y | y
Amanda | n | n
Sarah Harrison | n | n | y
Richard | y | y | y
Melanie | y | y | y
Ian Reid | n | y | y
Ian Douglas | Y | Y | Y
Katrina | y | n | y
Colin Cooper | Y | Y | Y
Matt | n | y | y
David | Y | Y - from 9:30 | Y from 11:00
| 9 | 10 | 13
Non Pay Star Chambers | Session 1 | Session 2 | Session 3
| 4th September | 10th September | 17th September
| 14:00 to 17:00 | 09:00 to 12:00 | 09:30 to 12:30
In Attendence | Debbie
| Annette | Annette | Annette
| Richard | Richard | Richard
| Sam (recording of savings) | Sam (recording of savings) | Sam (recording of savings)
Allocation of Slot | David | Matt | Sarah
| Ian D | Melanie | Wendy
| Katrina | Colin | Ian R
| Claira | Kate | Amanda
| Richard | Dawn

## Detailed Pay Budget Setting (hidden)
Not updated
Pay Budget Setting - Timetable - Corporate Accounting
Category of Activity | Activity | Responsible Team/Owner | Deadline | Deadline for Papers
Costings | Blank PSE/Officer/PCSO PBS costings file for 2025/26 to be created ready for populating. | HoFS/ATFS | 2023-09-01
Costings | Sense check of costing files to ensure no historical links, comments etc. | HoFS | 2023-09-01
Establishment | Initial download for PBS issued by Organisation Management (OM) | HR | 2023-09-01
Establishment | Establishment tables issued to HRAs/Heads of Dept./Command | FBPs/MAs | 2023-09-07
Establishment | Reminder to be sent with confirmation of deadline | FBPs/MAs | 2023-09-14
Establishment | First weekly tracker review (access to be given by Org Mgt). To be reviewed each Friday until first Friday in October. | HoFS | 2023-09-15
Establishment | Deadline for the return of completed establishment tables | HRAs/Heads of Dept./Command | 2023-09-21
Costings | Staff/Officers & PCSO costings file ready for review. Establishment reflective of HR download/trackers, Allowances/Pension/NI/Increment calculations complete. Summary table populated. | HoFS/ATFS | 2023-09-22
Costings | Agree format for Officer turnover calculations | MA Pay/HoFS | 2023-09-22
Establishment | Log any establishment changes and ensure HR to follow up before deadline of first Friday in October | FBPs/MAs | 2023-09-29
Costings | To review staff/officer costings file for formula errors and large variances to previous years file. | HoFS | 2023-09-29
Costings | To review PCSO costings file for formula errors and large variances to previous years file. | HoFS | 2023-09-29
Budget Preparation | Deadline for 2025/26 FYE Virements (Pay and non-pay) to Head of Finance for approval (via pending virements process) - Month 6 MMR deadline | All | 2023-09-29
Establishment | Deadline for last HR Tracker with approved changes. No further changes to be made without COG/Star Chamber approval. | All | 2023-10-06
Costings | Prepare budget/calculate turnover. | MA Pay/HoFS | 2023-10-06
Costings | Ensure all tracked changes are included on costings files, with reconcilation to original download | HoFS/ATFS | 2023-10-09
Costings | Circulate copy of costings for review by FBP&MA team | HoFS/ATFS | 2023-10-09
Establishment | Updated download for PBS issued by Organisation Management (OM) | HR | 2023-10-09
Costings | CFO review 1 of 2 | CFO/HoF/HoFS/MA Pay | 2023-10-10
Establishment | Version 2 of Establishment tables issued to HRAs/Heads of Dept./Command - referencing any changes from version 1 | FBPs/MAs | 2023-10-13
Establishment | Reconciliation of Establishment and Holding Codes (i.e. growth included on PBS and outstanding, recurring budget requirement for growth/PUP) | FBP - Strategic Change/HoFS | 2023-10-13
Costings | FBPs & MAs to review costing files for cost centres/POA, funding source (i.e. Force vs External) | FBPs/MAs | 2023-10-13
Costings | COG budget workshop provisional review (1 of 2) (no pay budgets) | HoF/HoFS | 2023-10-18
Costings | To review all costings files. | HoF | 2023-10-20
Costings | CFO review 2 of 2 | CFO/HoF/HoFS/MA Pay | 2023-10-23
Budget Preparation | Prepare 2025/26 Budget Build file, clear down prior pay budgets and ensure FYE included. | HoFS/ATFS | 2023-11-01
Costings | Draft Budget including PBS detail issued to CFO & DCC | HoFS | 2023-11-02
Finalisation | Verbal Budget update to Efficiency, Savings & Growth Board | CFO/HoF | 2023-11-07
Finalisation | COG budget workshop (2 of 2) to include Pay | CFO/HoF | 2023-11-15
Budget Preparation | Calculate pay allocations (to include averages for Officers & PCSOs) for review by MA(pay) | HoFS/ATFS | 2023-11-17
Budget Preparation | Send the growth & saving costing for coding to MAs/FBPs | HoFS/ATFS | 2023-11-17
Costings | Autumn Statement - assumptions update re NI thresholds App Levy etc | HoFS | Est mid - late Nov
Finalisation | CFOs/S151 Officer Briefing PFCC & CC | HoFS | 2023-11-21
Budget Preparation | Return coded growth bid & savings | FBPs/MAs | 2023-11-28
Budget Preparation | Populate budget build with pay allocations | HoFS/ATFS | 2023-12-01
Budget Preparation | Populate budget build with growth & savings and issue model to MAs/FBPs for review. | HoFS/ATFS | 2023-12-01
Pre upload | Build force growth into budget build | HoFS/ATFS/FBP Strategic Change | 2023-12-01
Budget Preparation | Send Budget Build file for review | HoFS/ATFS | 2023-12-04
Finalisation | PFCC & Chief Constable - discuss latest budget proposals | CFO | 2023-12-05 | 2023-11-23
Budget Preparation | Send any adjustments/changes to budget build to RTA (to include budget movements/POA changes) | FBPs/MAs | 2023-12-12
Finalisation | Strategic Board - Budget proposals | Strategic Change | 2023-12-14
Budget Preparation | Finalise budget build at subjective heading level - to include any FBP/MA changes | HoFS | 2023-12-15
Finalisation | COG: Review Chief Constable's Budget Proposal to PFCC (Post HO announcement) | CFO/HoF | 2023-12-19 | 2023-12-18
Budget Preparation | Confirm outcome of COG: Review Chief Constable's Budget Proposal to PFCC (Post HO announcement) | CFO/HoF | 2023-12-19
Finalisation | PFCC Engagment meeting PFCC, PFCC Chief Exec, CC, DCC, CFOs, | CFO/HoF | 2023-12-20 | 2023-12-19
Budget Preparation | Subjective summary of proposed budget to PFCC | HoFS | 2024-01-02
Finalisation | PFCC presents proposed budget at Police Fire and Crime Panel Budget setting Working group | CFO | 2024-01-04 | 2023-12-29
Budget Preparation | 2025/26 budget uploaded files prepared | HoFS/ATFS | 2024-01-19
Budget Preparation | 2025/26 Ready Reckoner produced | HoFS/ATFS | 2024-01-31
Budget Preparation | PFCC Panel approve budget | CFO/HoF | 2024-02-01
Pre upload | Confirm final budget agreed and any additional changes to Corporate Accounting | HoF | 2024-02-02
Pre upload | Budget build file frozen | HoFS | 2024-02-05
Finalisation | 2025/26 budget uploaded files updated for any changes | HoFS/ATFS | 2024-02-09
Finalisation | 2025/26 budget uploaded into SAP | HoFS/Corp Act | 2024-02-16
Finalisation | 2025/26 Draft internal budget book created | HoFS/ATFS | 2024-02-21
Finalisation | Distribute copy of 2025/26 internal budget book, report any mispostings back to Corporate Accounting - include review of SAP for completeness | FBPs/MAs | 2024-02-23
Finalisation | Mispostings corrected on SAP and internal budget book updated. | HoFS/Corp Act | 2024-02-28
Finalisation | Draft of Internal budget book sent to Head of Finance for review | HoFS | 2024-03-01
Finalisation | Prepare costings and budget build information for inclusion in establishment tables | HoFS/ATFS | 2024-03-06
Finalisation | To return Internal budget book with comments/feedback | HoF | 2024-03-13
Finalisation | 2025/26 Internal budget book sent to Budget Holders. | HoFS | 2024-03-15
Finalisation | 2025/26 Estabilshment tables (with budgets) sent to Budget Holders. | HoFS/FBPs/MAs | 2024-03-15
Finalisation | Load 2025/26 base budget (plan 2) on SAP | HoFS/Corp Act | 2024-03-29
Finalisation | 1st Draft of External budget book sent to Head of Finance for review | HOCA | TBC
Finalisation | To return external budget book with comments/feedback | HoF | TBC
Finalisation | 2nd draft external budget book sent to CFO for review. | HoFS | TBC
Finalisation | To return external budget book with comments/feedback | CFO | TBC
Formulas:
Deadline = [Deadline, row above]+7
Deadline = [Deadline, row above]

## Last Year's Timetable (hidden)
2020/21 Budget Setting - DETAIL
[5 empty] | P | P | P | P
| DATE | FORCE DEADLINES / ACTIVITY | OPFCC & EXTERNAL DEADLINES / ACTIVITY | CORPORATE FINANCE KEY DEADLINES / ACTIVITY | Time | Summary | Detail | Department | DB note
[5 empty] | X | X | X | X
| DATE | FORCE DEADLINES / ACTIVITY | OPFCC & EXTERNAL DEADLINES / ACTIVITY | CORPORATE FINANCE KEY DEADLINES / ACTIVITY | X | P | P | P |  | Notes to Assist with Next Year's timetable
| 1. Information Gathering & Reviewing - Detail |  |  |  |  | P | P | P
1. Information Gathering & Reviewing - Detail | 2019-07-04 | SLT: 2020/21 Budget Setting Timetable - presentation by Corporate Finance. |  | Budget timetable presentation at SLT. |  | P | P | P
| 2019-07-15 | Strategic Change Co-Ordination Board. |  |  |  | P | P | P
| 2019-07-15 | Capital project leads receive capital bids/business case template. |  | Issue capital bids/business case template. | End of day | P | P | P
| 2019-07-15 | Budget holders receive Revenue Budget Change (RBC) templates. |  | Issue RBC template for Contractual Cost Pressure, Service Demand Change, New Revenue Investment, non-pay savings & inflation changes. | End of day | P | P | P | includes Ready Recknor
| 2019-07-19 | Deadline for return of savings plans for review at Efficiency & Savings Board on 26th July. |  | Receive savings plans |  | P | P | P
| 2019-07-26 |  |  | Officers averages pay allocations review. |  |  | P | P
| 2019-07-26 | Efficiency & Savings Board - July. |  |  |  | P | P | P
| 2019-08-12 |  | Estates Strategic Board. |  | End of day | P | P | P
| 2019-08-19 | Deadline for provisional Capital and Revenue Budget Changes bids to be sent to Corporate Finance. |  | Receive provisional Capital and Revenue Budget Changes bids from budget holders / project managers. | End of day | P | P | P
| 2019-08-22 | SLT: 2020/21 Budget Setting: Verbal update by Corporate Finance. |  | Budget update at SLT. |  | P | P | P
| TBC | Efficiency & Savings Board - August. |  |  |  | P | P | P
| 2019-08-16 |  |  | Send to CFO draft of MTFS & Strategic view for COG meeting on 28th Aug. | Mid day |  |  | P
| 2019-08-21 |  |  | Send MTFS & strategic view for COG meeting next week | 10am |  |  | P
| 2019-08-28 | COG: MTFS & strategic view presented (MTFS & strategic view of provisional revenue and capital proposals) for presentation to Strategic Board on 16th September. |  | Present MTFS & strategic view of revenue and capital proposals at COG. | End of day | P | P | P
| 2019-08-30 | Strategic Change Co-Ordination Board. |  |  |  | P | P | P
| 2019-09-02 |  |  | Officer, Staff & PCSO establishment extracted from HR system for pay budget setting (version 1) – as at 1st September 2019. |  |  | P | P
| 2019-09-03 | Budget holders receive non-pay financial information based on August (month 5) forecast. |  | Issue financial non-pay information to budget holders. | End of day |  | P | P
| 2019-09-04 |  |  | Send draft of MTFS & strategic view for Strategic Board 16th Sept to CFO | Mid day |  |  | P | Includes non-pay details of force activity for last 3 years, original budget, current budget and base budget for next year
| 2019-09-04 | Efficiency & Savings Board. |  |  |  | P | P | P
| 2019-09-06 |  |  | Corporate Finance Non Pay & Capital Star Chamber: 1 of 3. |  |  | P | P
| 2019-09-06 | Force Growth Programme Board: Initial Strategic discussion on priorities for investment should Precept/Police Grant Growth become available . |  |  |  | P | P | P
| 2019-09-09 |  |  | Send MTFS & strategic view for Strategic Board next week | Mid day |  |  | P
| 2019-09-09 | Heads of Departments/Commands & HR Advisors receive establishment (version 1). |  | Issue establishment version 1 to HR Advisors and Heads of Department/Commands. | End of day |  | P | P
| 2019-09-09 | SSD Savings Workshop |  |  |  |  | P | P
| 2019-09-10 |  |  | Corporate Finance Non Pay & Capital Star Chamber: 2 of 3. | End of day |  | P | P
| 2019-09-13 | Deadline for final Capital and Revenue Budget Changes bids to be sent to Corporate Finance. |  |  | End of day | P | P | P
| 2019-09-16 | Strategic Board: MTFS presented & initial strategic view of revenue and capital proposals, including a verbal update of latest proposals. | Strategic Board: MTFS presented & initial strategic view of revenue and capital proposals, including a verbal update of latest proposals. |  | End of day | P | P | P
| 2019-09-17 |  |  | Corporate Finance Non Pay & Capital Star Chamber: 3 of 3. |  |  | P | P
| 2019-09-20 | Establishment version 1 returned by HR Advisors and Heads of Departments/Commands. |  | Receive establishment version 1 from Heads of Department/Commands. | End of day |  | P | P
| 2019-09-20 |  |  | Draft COG workshop information sent to CFO. | End of day |  |  | P
| 2019-09-26 |  | Performance & Resources Board |  |  | P | P | P
| 2019-09-26 | Strategic Change savings plan sent to Corporate Finance. |  | Receive Strategic Change savings plan. | End of day |  | P | P
| 2019-09-27 |  |  | Draft COG budget setting folder information sent to CFO. | Mid day |  |  | P
| 2019-10-02 | Risk Star Chamber: Initial consideration of growth interdependencies and mitigation of Strategic Risk. |  |  |  | P | P | P
| 2019-10-02 |  |  | Send budget folder information – to include Provisional Capital & Revenue bids, savings and MTFS (for COG 9th Oct.). | 10am |  |  | P
| 2019-10-04 | COG receive 2020/21 budget papers containing Provisional Capital & Revenue bids, savings and MTFS for budget workshop on 9th Oct. |  |  | End of day | P | P | P
| 2019-10-07 | Strategic Change Co-Ordination Board. |  |  | End of day | P | P | P
| 8th Oct - TBC |  |  | CFO review of draft provisional pay budget setting information (1 of 2) |  |  |  | P
| 2019-10-09 | COG: Budget Workshop (1 of 2) – review of provisional Capital & Revenue bids, savings and MTFS (at headquarters - three hours agenda item?) |  | Attend COG workshop |  | P | P | P
| DATE | FORCE DEADLINES / ACTIVITY | OPFCC & EXTERNAL DEADLINES / ACTIVITY | CORPORATE FINANCE KEY DEADLINES / ACTIVITY | X | P | P | P
| 2. Building the Budget - Detail |  |  |  |  | P | P | P
2. Building the Budget - Detail | TBC (last year 29th Oct) |  | Chancellors Autumn Budget Statement. |  |  | P | P | P
| 2019-10-11 |  |  | Deadline for COG approved establishment changes to be sent to Organisational Management team to be included in pay budget setting. Any COG approvals after this date will require a RBC proposal. |  |  | P | P
| 2019-10-14 | Efficiency & Savings Board. |  |  |  | P | P | P
| 16th Oct - TBC |  |  | Strategic Change review of pay budget setting establishment (staff and officers) |  |  | P | P
| 2019-10-17 | SLT: Budget Setting update - verbal report. |  |  |  | P | P | P
| 2019-10-18 | Force Growth Programme Board - Review of scalable growth bids requested following 1st COG Budget workshop. Increase in Infrastructure support costs to support/enable growth will also be reviewed. |  |  |  | P | P | P
| 24th Oct TBC |  |  | CFO review of draft provisional pay budget setting information (2 of 2). |  |  |  | P
| 2019-10-24 |  | Police, Fire and Crime Panel |  |  | P | P | P
| 2019-10-28 | Capital Management Board. |  | Attend Capital Management Board. |  |  | P | P
| 2019-10-31 |  | Performance & Resources Board |  |  | P | P | P
| 2019-11-01 | CFO receives Provisional Pay Budgets. |  | Pay Budgets issued to CFO. | End of day |  | P | P
| 2019-11-07 |  |  | Draft COG report sent to CFO for 20th November workshop. | End of day |  |  | P
| 8th Nov |  | Receive précis of Capital & Revenue Budget Change bids, MTFS and savings report to OPFCC for 14th Nov meeting. | Send précis of Capital & Revenue Budget Change bids, MTFS and savings report to OPFCC for 14th Nov meeting | Mid day |  | P | P
| 2019-11-14 |  | Meeting to review a précis of Capital & Revenue budget increase bids, savings and MTFS presented to OPFCC by DCC and CFO of CC/Chief Accountant. |  | End of day | P | P | P
| 2019-11-14 |  |  | Send papers for COG Budget Review Workshop on 20th November. | 10am |  |  | P
| 2019-11-18 |  | Estates Strategic Board. |  | End of day | P | P | P
| 2019-11-20 | COG: Budget Review Workshop (2 of 2) – includes 2020/21 Budget Summary & MTFS (first review with pay budget information) (at headquarters - three hour agenda item?) |  | Attend COG workshop | End of day | P | P | P
| 2019-11-22 |  |  | Draft COG report sent to CFO for 4th December (Draft Chief Constable proposal). | Mid day |  |  | P
| 2019-11-22 | Chief Constable receives updated budget information following COG on 20th Nov for meeting with PFCC on 25th Nov (date tbc). |  | Send to Chief Constable (cc DCC) updated budget information following COG on 20th Nov for meeting with PFCC on 25th Nov (date tbc). |  |  | P | P
| 2019-11-25 |  | PFCC & Chief Constable meeting to discuss latest budget setting position. |  |  | P | P | P
| 2019-11-26 | Strategic Change Co-Ordination Board. |  |  | End of day | P | P | P
| 2019-11-27 |  |  | Send Draft Chief Constable Budget Proposal Report for COG on 4th Dec. | 10am |  |  | P
| 2019-11-28 |  | Performance & Resources Board - verbal budget update |  |  | P | P | P
| 2019-11-29 | Force Growth Programme Board: Review and update of Growth Investment proposals. |  |  |  | P | P | P
| 2019-12-03 | Risk Star Chamber: To consider growth interdependencies and mitigation of Strategic Risk. |  |  |  | P | P | P |  | there was no risk star chamber in December
| 2019-12-04 | COG: Review Chief Constable's Budget Proposal to PFCC (pre HO announcement) for Strategic Board on 9th December. |  | Present draft of Chief Constables budget proposal to PFCC (pre HO announcement). |  | P | P | P
| 2019-12-05 |  | Receive OPFCC Chief Constable's presentation to PFCC on 2020/21 draft budget proposal (pre HO announcement). | Send to OPFCC Chief Constable's presentation to PFCC on 2020/21 draft budget proposal (pre HO announcement). | End of day |  | P | P |  | this was sent on 17th December due to delayed funding announcement
| 2019-12-05 |  | Police, Fire and Crime Panel |  |  | P | P | P |  | Budget was not on the agenda for this meeting
| 2019-12-09 | Efficiency & Savings Board. |  |  | End of day | P | P | P
| DATE | FORCE DEADLINES / ACTIVITY | OPFCC & EXTERNAL DEADLINES / ACTIVITY | CORPORATE FINANCE KEY DEADLINES / ACTIVITY | X | P | P | P
| 3. Budget & Precept Proposal - Detail |  |  |  |  | P | P | P
3. Budget & Precept Proposal - Detail | During December (last year 13th Dec) |  | Home Office Police Grant announcement. |  | End of day | P | P | P |  | received 22nd January 2020
| 2019-12-09 |  | Strategic Board: Chief Constable's presentation to PFCC on 2020/21 draft budget proposal (pre HO announcement). | Attend Strategic Board | End of day | P | P | P |  | Budget was not presented to this board due to delayed Home Office Announcement - went to extraordinary meeting on 19th Dec
| 2019-12-13 | Strategic Change Team to send reasons for increase in precept to CFO. |  |  |  | P | P | P |  | not relevant for 20/21 budget setting
| 2019-12-18 | COG: Budget update (post HO grant announcement). |  |  | End of day | P | P | P
| 2019-12-19 |  | Extraordinary Strategic Board: Chief Constable's presentation to PFCC on 2020/21 draft budget proposal (pre HO announcement). | Information for budget proposal letter to be sent to CFO. |  |  |  | P
| 2019-12-20 |  | Performance & Resources Board - verbal budget update |  |  | P | P | P
| 2019-12-20 | COG receive draft of Chief Constables budget proposal letter (post HO grant announcement - Corporate Finance to co-ordinate letter). |  | Send draft of Chief Constables budget proposal letter (post HO grant announcement - CFO to co-ordinate letter). | End of day | P | P | P |  | did not go to COG for 20/21 budget setting due to funding announcement delays
| 2020 |  |  |  |  | P | P | P
| TBC |  | Business community consultation (Treasurer). |  | End of day | P | P | P |  | this happened but not sure of the date
| During January & February |  |  | Build budget and load onto SAP (subject to 2019/20 Closure timetable). | End of day |  | P | P
| 2020-01-02 | Final draft of Chief Constable's budget proposal letter to be sent to Chief Officers (initial draft sent on 20th Dec - Corporate Finance to co-ordinate letter). |  |  | End of day | P | P | P |  | This did not happen due to delays in funding announcement
| 2020-01-03 | COG: Final review of Chief Constable's budget proposal letter (sent on 20th Dec - Corporate Finance to co-ordinate letter). |  |  |  | P | P | P |  | This did not happen due to delays in funding announcement
| 2020-01-02 |  | Meeting to discuss 2020/21 Budget Proposal letter from Chief Constable with Chief Constable and CFO of the Chief Constable. |  |  | P | P | P
| 2020-01-03 | 2020/21 Budget Proposal letter sent to PFCC from Chief Constable (post HO announcement - Corporate Finance to co-ordinate letter). | PFCC receives 2020/21 Budget letter from Chief Constable (post HO announcement). |  | End of day | P | P | P |  | sent on 23rd Jan 20. The day following the funding announcement
| 2020-01-15 |  | Receive budget papers (appendices) for PFC Panel from Corporate Finance. | Send to OPFCC the contributing papers (i.e. appendices) for PFC Panel budget setting report. | End of day | P | P | P |  | sent on 23rd Jan 20. The day following the funding announcement
| 2020-01-15 |  | Send to ECC the budget report to be presented at PFC Panel. |  | Mid day | P | P | P
| 2020-01-22 |  | PFCC presents proposed budget and precept to PFC Panel (1). |  |  | P | P | P
| By 8th Feb |  | PFC Panel to review and respond to PFCC (2) (if PFC Panel members not responded at January PFC Panel). |  |  |  | P | P
| By 15th Feb |  | PFCC to respond to the PFC Panel with revised precept (if required) (3). |  |  |  | P | P
| By 22nd Feb |  | PFC Panel to review revised precept and respond to PFCC (4). |  |  |  | P | P
| Before 1st March |  | PFCC responded to PFC Panel second report and (revised) precept (5). |  |  |  | P | P
| TBC |  | PFCC informs Billing Authorities of precept. |  |  | P | P | P
| 2020-03-02 | Efficiency & Savings Board - - commence main review of 2021/22 savings (with view of going to COG in March) |  |  | End of day | P | P | P
| 4. Post Budget & Precept Setting - Detail | [5 empty] | P | P
4. Post Budget & Precept Setting - Detail | One day after budget set |  |  | Growth and savings summary sent to Departments and Commands (i.e. appendices from Chief Constables budget proposal letter - updated for any final changes . | End of day |  | P | P
| tbc | Efficiency & Savings Board - February. |  |  |  |  | P | P
| During February / March |  |  | Review budgets on SAP and prepare budget books (subject to 2019/20 Closure timetable). |  |  | P | P
| Mid Feb - TBC | COG: SCT – Presents Growth implementation plan for 2020/21 Precept Growth |  |  |  |  | P | P
| tbc |  | PFCC sends CTAX leaflet to Billing Authorities. |  |  |  | P | P
| Mid Mar - TBC | Strategic Board: Present Growth Implementation plan to OPFCC | Strategic Board: Growth Implementation plan presented to OPFCC
| tbc | Efficiency & Savings Board - March |  |  |  |  | P | P
| End of Mar |  | Police & Crime Panel: OPFCC present Growth plan to Police & Crime Panel
| 2020-03-31 |  |  | Budgets issued to budget holders (Internal Budget Book and individual growth and savings by budget holder). |  |  | P | P
| 2020-04-01 | New Financial Year. |  |  |  |  | P | P
7

## Strategic Timetable
Strategic - Timetable
Budget Version
PFCC S151 Category | Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Date | 1. June Strategic Board | 2. Sept Strategic Board | 3. COG Workshop 1 and PFCC Update | 4. Dec Strategic Board | 5. Post HO Funding Announcement | 6. Police, Fire, Crime Panel | Comments
Strat Board | ST1 | Strategic | March Strategic Board - Paper Deadline | Corporate Finance | Debbie Martin | 2024-02-23 | [6 empty] | Send MTFS (Q4 based on Month 10 & Prior Year Budget Setting) to PFCC for Strategic Board
Strat Board | ST2 | Strategic | Strategic Board - March | Corporate Finance | Debbie Martin | 2024-03-05 | [6 empty] | 2025/26 Draft Budget Setting Timetable and MTFS (Q4 based on Month 10 & Prior Year Budget Setting papes) presented to Strategic Board
Internal | ST3 | Strategic | Review of budgets with increased cost pressures (pay and non-pay) | Corporate Finance | Debbie Martin | 2024-05-17 | [6 empty] | Conclude work to identify baked in costs (areas of policy or statutory changes resulting in increased costs) E.g. impact of accreditations, for inclusion in MTFS Q1
Strat Board | ST4 | Strategic | Meeting with PFCC S151 Officer re MTFS Q1 | Corporate Finance | Debbie Martin / Janet Perry | 2024-05-20 | [6 empty] | Meeting to discuss MTFS Q1 ahead of COG report being finalised
Internal | ST5 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-05-22 | [6 empty] | Paper deadline for MTFS Q1
Strat Board | ST6 | Strategic | MTFS Supporting Spreadsheets provided to PFCC Section 151 Officer | Corporate Finance | Annette Chan | 2024-05-23 | [6 empty] | Working papers to support MTFS Q1
Internal | ST7 | Strategic | COG - MTFS Q1 Update | Corporate Finance | Debbie Martin | 2024-05-29 | [6 empty] | MTFS Q1 presented to COG.
PFCC Engage | ST8 | Strategic | PFCC Engagement - send papers | Corporate Finance | Debbie Martin / Annette Chan | 2024-05-29 | [6 empty] | Send MTFS Q1 draft Strategic Board Report.
PFCC Engage | ST9 |  | PFCC Engagement - Meeting (June) | Corporate Finance | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2024-06-03 | [6 empty] | Pre-meet for the Q1 MTFS position ahead of Strategic Board
Strat Board | ST10 | Strategic | June Strategic Board - Paper Submission | Corporate Finance | Debbie Martin | 2024-06-07 | [6 empty] | Send MTFS Q1 to PFCC for Strategic Board - This is outside the normal deadline for papers of 30th May but allows for PFCC engagement on 3rd June.
Strat Board | ST11 | Strategic | Strategic Board - June | Corporate Finance | Debbie Martin | 2024-06-10 | [6 empty] | MTFS (Q1) & Updated Budget Setting Timetable presented to Strategic Board (based on reports presented to COG on 15th and 29th May). Draft paper to be circulated to PFCC Office 7th June.
Internal | ST132 | Strategic | Timetable distributed to Budget Holders | Corporate Finance | Annette Chan | 2024-06-11 | [6 empty] | Budget Setting Timetable distributed to Budget Holders
| ST13 | Strategic | COG - Briefing and progress update on the Continuous Improvement Programme. | Continuous Improvement & Analytics | DCC Andrew Prophet | 2024-06-12
Internal | ST14 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-06-19 | [6 empty] | Paper deadline for MTFS June Monthly Update
Internal | ST15 | Strategic | COG - MTFS Update | Corporate Finance | Debbie Martin | 2024-06-26 | [6 empty] | MTFS Monthly Update
| ST16 | Strategic | Police, Fire & Crime Panel Meeting (Paper Deadline) | PFCC | Janet Perry | 2024-07-10 | [6 empty] | Presentation of Budget Setting Paper describing activities and process/timetable for budget setting - Paper Deadline
Internal | ST17 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-07-10 | [6 empty] | Paper deadline for MTFS July Monthly Update
Panel | ST18 | Strategic | Police, Fire & Crime Panel Meeting paper Info to the PFCC (final updates) | Corporate Finance | Debbie Martin | 2024-07-11 | [6 empty] | Will form basis of papers going to Police, Fire & Crime Panel 3rd October
| ST19 | Strategic | Extraordinary Strategic Board (Continuous Improvement Programme) | Continuous Improvement & Analytics | DCC Andrew Prophet | July 24 (TBC)
Internal | ST20 | Strategic | COG - MTFS Update | Corporate Finance | Debbie Martin | 2024-07-24 | [6 empty] | MTFS Monthly Update and decisions on investment bids to be progressed.
| ST21 | Strategic | Police, Fire & Crime Panel Meeting | PFCC | PFCC | 2024-07-25 | [6 empty] | Presentation of Budget Setting Paper describing activities and process/timetable for budget setting
Internal | ST22 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-08-14 | [6 empty] | Paper deadline for MTFS August Monthly Update
Internal | ST23 | Strategic | COG - MTFS Update | Corporate Finance | Debbie Martin | 2024-08-21 | [6 empty] | MTFS Monthly Update
Strat Board | ST24 | Strategic | Meeting with PFCC S151 Officer re MTFS Q2 | Corporate Finance | Debbie Martin / Janet Perry | 2024-09-02 | [6 empty] | Meeting to discuss MTFS Q2 going to Sept Strategic Board ahead of COG report being finalised
Strat Board | ST25 | Strategic | MTFS Supporting Spreadsheets provided to PFCC Section 151 Officer | Corporate Finance | Annette Chan | 2024-09-03 | [6 empty] | Working papers to support MTFS Q2
Internal | ST26 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-09-11 | [6 empty] | Paper deadline for MTFS Q2 report to COG on 18th Sept
Internal | ST27 | Strategic | Efficiency Savings and Growth Board | Strategic Change | Anna Hook | 2024-09-12 | [6 empty] | Overall savings proposals from commands prior to 7P Assessment agreed for inclusion in the next stage of the budget setting process.
Panel | ST28 | Strategic | Police, Fire & Crime Panel Meeting paper deadline | PFCC | Janet Perry | 2024-09-18 | [6 empty] | Papers will be based on June Strategic Board position
Internal | ST29 | Strategic | COG - MTFS, Investment and Savings Update | Corporate Finance | Debbie Martin | 2024-09-18 | [6 empty] | Update of MTFS Q2 presented to COG with high level view of Investment and Savings. Would include latest position submitted for Efficiency and Savings Board on 12th September.
PFCC Engage | ST30 | Strategic | PFCC Engagement - send papers | Corporate Finance | Debbie Martin / Annette Chan | 2024-09-19 | [6 empty] | Send MTFS Q2 draft Strategic Board Report.
PFCC Engage | ST31 | Strategic | PFCC Engagement - Meeting (Sept) | Corporate Finance | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2024-09-20 | [6 empty] | Pre-meet for the Q2 MTFS position ahead of Strategic Board
Strat Board | ST32 | Strategic | September Strategic Board - Paper Submission | Corporate Finance | Debbie Martin | 2024-09-23 | [6 empty] | Send MTFS Q2 paper to PFCC for Strategic Board. Normal paper deadline for board is Friday 13th Sept. Engagement meeting would have been held on 20th Sept.
Strat Board | ST33 | Strategic | Strategic Board - Sept | Corporate Finance | Debbie Martin | 2024-09-24 | [6 empty] | MTFS (Q2) presented to Strategic Board (based on report presented to COG on 18th Sept).
Working Group | ST34 | Strategic | Provision of Papers to PFCC Office for the PF&CP Budget Working Group (1) | Corporate Finance | Debbie Martin | 2024-09-30 | [6 empty] | Will form basis of papers going to Budget Working Group (1) in Oct
Panel | ST35 | Strategic | Police Fire and Crime Panel Meeting | PFCCs Office | PFCCs Office | 2024-10-03 | [6 empty] | Based on June Strategic Board position.
Internal | ST36 | Strategic | SCCB (Extraordinary Budget Setting Meeting) | Force Commands/Strategic Change | Chief Officers / Anna Hook | 2024-10-07 | [6 empty] | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
Working Group | ST37 | Strategic | Provision of Papers to panel working group (1) | PFCCs Office | Janet Perry | 2024-10-09 | [6 empty] | Papers based on Sept Strategic Board.
Working Group | ST38 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (1) | PFCCs Office | PFCCs Office | 2024-10-10 | [6 empty] | PFCC Engagement with the Police, Fire and Crime Panel, Budget Setting Working Group.
Internal | ST39 | Strategic | Draft Budget (Exc Pay) sent to CFO | Corporate Finance | Annette Chan | 2024-10-11 | [6 empty] | First draft of budget model consolidating current growth and savings (excluding pay budgets) provided to CFO
Internal | ST40 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-10-11 | [6 empty] | Paper deadline for COG Budget Workshop 1 or 2. (Revenue + Capital Bids, savings and MTFS - Excludes Pay)
Internal | ST41 | Strategic | COG - Budget Workshop 1 (exc. Pay) | Corporate Finance | Debbie Martin / Annette Chan | 2024-10-16 | [6 empty] | COG Budget Workshop (1 of 2) – review of provisional Capital & Revenue investment, savings and MTFS. Pay budgets not included.
PFCC Engage | ST42 | Strategic | Meeting with PFCC S151 Officer for PFCC Engagement Meeting | Corporate Finance | Debbie Martin / Janet Perry | 2024-10-18 | [6 empty] | Meeting with PFCC S151 Officer post October Budget Workshop (Excluding Pay)
Internal | ST43 | Strategic | Outcome of Decisions communicated to Budget Holders | Corporate Finance | Jenny Sayle | 2024-10-21 | [6 empty] | Outcome of decisions from COG Budget Workshop 1 communicated to Budget Holders (including bids approved and rejected)
Internal | ST44 | Strategic | Chancellors Autumn Budget Statement | N/A | N/A | W/C 21st Oct (estimated)
| ST45 | Strategic | MTFS Supporting Spreadsheets provided to PFCC Section 151 Officer |  |  | 2024-10-22 | [6 empty] | MTFS updated following COG Workshop 1. Supporting spreadsheets provided to PFCC S151 Officer after sharing with COG
PFCC Engage | ST46 | Strategic | PFCC Engagement - send papers | Corporate Finance | Debbie Martin / Annette Chan | 2024-10-22 | [6 empty] | Send Capital & Revenue Budget investment, MTFS and savings report to PFCCs Office for Engagement Meeting (Post COG Workshop)
PFCC Engage | ST47 | Strategic | PFCC Engagement - Meeting (Oct) | Corporate Finance | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2024-10-25 | [6 empty] | Meeting with PFCCs Office to review a précis of Capital & Revenue investment, savings and MTFS. Attended by DCC & CC. - Post COG Workshop
Working Group | ST48 | Strategic | Provision of any updates to PFCC Office for the PF&CP Budget Working Group (2) | Corporate Finance | Debbie Martin | 2024-10-29 | [6 empty] | Will form basis of papers going to Budget Working Group (2) on 30th Oct
Working Group | ST49 | Strategic | Provision of Papers to panel working group (2) | PFCCs Office | Janet Perry | 2024-10-31 | [6 empty] | Papers based on 1st COG Workshop
Internal | ST50 | Strategic | Draft Budget (inc Pay) sent to CFO | Corporate Finance | Annette Chan | 2024-10-31 | [6 empty] | Second draft of budget (incorporating pay budgets) provided to CFO
Panel | ST51 | Strategic | Police, Fire & Crime Panel Meeting paper Info to the PFCC | Corporate Finance | Debbie Martin | 2024-11-01
Working Group | ST52 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (2) | PFCCs Office | PFCCs Office | 2024-11-05
Internal | ST53 | Strategic | Efficiency, Savings and Growth Board | Corporate Finance | CFO/Head of Finance | 2024-11-05 | [6 empty] | Verbal budget update to Efficiency and Savings Board
Internal | ST54 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2024-11-06 | [6 empty] | Paper deadline for COG Budget Workshop 2 or 2. (Consolidated budget proposals with Pay)
Internal | ST55 | Strategic | Review of PFCC Budgets (including Pay) | Corporate Finance / PFCC Office | Annette Chan | 2024-11-11 | [6 empty] | Opportunity for PFCC office to review the detailed make-up of calculated 25/26 budget requirement including pay budget setting.
Internal | ST56 | Strategic | COG - Budget Workshop 2 (inc Pay) | Corporate Finance | Debbie Martin/Annette Chan | 2024-11-13 | [6 empty] | COG Budget Workshop (2 of 2 inc. pay) – review of provisional Capital & Revenue investement, savings and MTFS. Includes pay and allocation of officer overtime budgets
Internal | ST57 | Strategic | Outcome of Decisions communicated to Budget Holders | Corporate Finance | Jenny Sayle | 2024-11-18 | [6 empty] | Outcome of decisions from COG Budget Workshop 2 communicated to Budget Holders (including bids approved and rejected)
Panel | ST58 | Strategic | Police Fire and Crime Panel Meeting - Paper Deadline | PFCCs Office | PFCCs Office | 2024-11-20
Internal | ST59 | Strategic | Commissioners Precept Survey | PFCC | Darren Horsman | Nov (closing in December) | [6 empty] | PFCC has a duty to consult on the precept. Date not set but held as a place holder
Strat Board | ST60 | Strategic | Meeting with PFCC S151 Officer for PFCC Engagement Meeting | Corporate Finance | Debbie Martin / Janet Perry | 2024-11-21 | [6 empty] | Meeting to discuss MTFS Q3 going to December Strategic Board ahead of COG report being finalised
PFCC Engage | ST61 | Strategic | MTFS Supporting Spreadsheets provided to PFCC Section 151 Officer | Corporate Finance | Annette Chan | 2024-11-25
Panel | ST62 | Strategic | Police Fire and Crime Panel Meeting | PFCCs Office | PFCCs Office | 2024-12-05
Internal | ST63 | Strategic | COG - Review of Budget Letter | Corporate Finance / Strategic Change | Debbie Martin / Anna Hook | 2024-12-11 | [6 empty] | COG review first draft of budget letter
Internal | ST64 | Strategic | Home Office Funding Announcement | N/A | N/A | 12/12/2024 - Estimated
PFCC Engage | ST65 | Strategic | PFCC Engagement - send papers for Dec meeting | Corporate Finance | Debbie Martin / Annette Chan | 2024-12-12 | [6 empty] | Papers based on latest position (including pay)
Panel | ST66 | Strategic | Preliminary Findings of precept survey provided to PFCC and S151 Officer | PFCCs Office | Darren Horsman | 2024-12-12
PFCC Engage | ST67 | Strategic | PFCC Engagement - Meeting (Nov) | Force | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2024-12-16 | [6 empty] | PFCC & Chief Constable meeting to discuss latest budget setting position.
Internal | ST68 | Strategic | COG Paper Deadline for -Chief Constable's Budget Proposal | Corporate Finance | Debbie Martin | 2024-12-16 | [6 empty] | DM to co-ordinate with input from Strategic Change and Chief Officers. Letter to be finalised for COG virtual review on 19th Dec.
Strat Board | ST69 | Strategic | MTFS Supporting Spreadsheets (Final Update) provided to PFCC Section 151 Officer | Corporate Finance | Annette Chan | 2024-12-16 | [6 empty] | Working papers to support MTFS Q3 (reflecting any updates from the PFCC Engagement Meeting)
Strat Board | ST70 | Strategic | Strategic Board - Send Chief Constable Budget Proposal | Corprate Finance | Debbie Martin | 2024-12-17 | [6 empty] | Draft Budget Proposal sent to PFCC Office (PM). Normal paper deadline is the 10th December.
Strat Board | ST71 | Strategic | Strategic Board (Dec) - Budget Proposals & Officer Investment (Prior to HO Funding Announcement) | Strategic Change | Debbie Martin / Anna Hook | 2024-12-19 | [6 empty] | Strategic Board - Chief Constable presents Budget Proposals including Officer investment (Prior to HO Funding Announcement)
Internal | ST72 | Strategic | Update Capital for approved projects from the December Strategic Board (Capital Programme/Rev Cons/Revenue cost of financing) | Corporate Accounting | Matt Tokley | 2024-12-20 | [6 empty] | Capital position will require updating to feed into budget proposal going to COG Virtual on 23rd December
Working Group | ST73 | Strategic | Meeting with PFCC S151 Officer for update post funding announcement | Corporate Finance | Debbie Martin / Janet Perry | 2024-12-20 | [6 empty] | To discuss impact of funding settlement for inclusion in text for working group meeting.
PFCC Engage | ST74 | Strategic | PFCC Engagement - Meeting (Dec) | Chief Constable | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2024-12-20 | [6 empty] | MTFS/Budget Setting Review post Home Office Funding Announcement (inc adherence to Police, Fire and Crime Plan) - Includes near final draft of Chief Constable's letter
Internal | ST75 | Strategic | COG Virtual: Review Chief Constable's Budget Proposal to PFCC (Post HO announcement) | Corporate Finance | Debbie Martin | 2024-12-23 | [6 empty] | Virtual Review of Budget post HO Funding Announcement
PFCC Engage | ST76 | Strategic | PFCC Engagement Meeting - Paper Deadline (Notification of changes following COG Virtual review) | Corporate Finance | Debbie Martin | 2024-12-23 | [6 empty] | Papers for engagement meeting on 24th Dec and Budget Working Group on 31st Dec.
Working Group | ST77 | Strategic | Provision of Updated Papers to PFCC Office for the PF&CP Budget Working Group (3) - inc . Impact of funding announcement | Corporate Finance | Debbie Martin | 2024-12-24 | [6 empty] | Will form basis of papers going to Budget Working Group (3) - Based on Q3 MTFS with reference to Funding Announcement impacts in text
Working Group | ST78 | Strategic | Provision of Papers to panel working group (3) | PFCCs Office | Janet Perry | 2024-12-30 | [6 empty] | Papers based on info post HO Funding announcement.
PFCC Engage | ST79 | Strategic | PFCC Engagement - send papers | Corporate Finance | Debbie Martin / Annette Chan | 2025-01-03 | [6 empty] | Send latest budget setting position to PFCCs Office for Engagement Meeting. Include updates from Dec Engagement meeting
PFCC Engage | ST80 | Strategic | PFCC Engagement - Meeting (Jan) | Chief Constable | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2025-01-06 | [6 empty] | Chief Constable meets with PFCC to discuss Chief Constable's Budget letter
Working Group | ST81 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (3) | PFCCs Office | PFCCs Office | 2025-01-07 | [6 empty] | Papers based on those presented to December Strategic Board
Working Group | ST82 | Strategic | Provision of Papers to PFCC CFO for the PF&CP Budget Working Group (4) | Corporate Finance | Debbie Martin | 2025-01-07 | [6 empty] | Papers for working group (supporting spreadsheets)
Internal | ST83 | Strategic | COG - Final review of Chief Constable's budget proposal letter | COG | COG Members | 2025-01-08 | [6 empty] | COG: Final review of Chief Constable's budget proposal letter post HO funding announcement. (Virtual) - to include Appendicies with subjective summary
Panel | ST84 | Strategic | Final Precept survey provided to PFCC and S151 Officer | PFCCs Office | Darren Horsman | 2025-01-09
PFCC Engage | ST85 | Strategic | Chief Constable sends final budget proposal letter and appendicies to PFCC | Corporate Finance | Debbie Martin / Annette Chan | 2025-01-10 | [6 empty] | Budget Proposal letter sent to PFCC from Chief Constable (With Supporting Appendicies inc. Subjective Summary)
Working Group | ST86 | Strategic | Provision of papers to working group (4) | PFCCs Office | Janet Perry | 2025-01-13
Working Group | ST87 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (4) | PFCCs Office | PFCCs Office | 2025-01-14
Panel | ST88 | Strategic | PFC Panel Papers - sent to ECC | PFCCs Office | Janet Perry | 2025-01-22 | [6 empty] | Panel papers including PFCC response to Chief Constable letter sent to ECC for panel.
Panel | ST89 | Strategic | Police Fire & Crime Panel | PFCCs Office | PFCC | 2025-02-04 | [6 empty] | PFCC presented budget to panel
Internal | ST90 | Strategic | Circulation of Info to Budget Holders | Corporate Finance | Annette Chan | 2025-02-07 | [6 empty] | Circulated for information ahead of Internal Budget Book. (Investment Bids, Savings and Capital included in budget presented to panel)
Internal | ST91 | Strategic | PFCC informs Billing Authorities of precept. | PFCCs Office | PFCC S151 Officer | 2025-02-07
Panel | ST92 | Strategic | Police Fire & Crime Panel (Reserve Date) | PFCCs Office | PFCC | 2025-02-18
Internal | ST93 | Strategic | Ready Reackoner Rates Calculated | Corporate Finance | Financial Performance & Reporting | 2025-02-28 | [6 empty] | Rates to be used for new year business cases.
Internal | ST94 | Strategic | Internal Budget Book | Corporate Finance | Corporate Accounting | 2025-02-28 | [6 empty] | Circulation of Internal Budget Book to Budget Holders
Internal | ST95 | Strategic | Establishment Reports | Corporate Finance | Corporate Accounting | 2025-02-28 | [6 empty] | Establishment Reports circulated to Budget Holders
Strat Board | ST96 | Strategic | Strategic Board -March | Corporate Finance | Debbie Martin | March 2025 (TBC) | [6 empty] | Approval of 2025/26 Budget (including POA Analysis) and MTFS including accompanying Decision Report
Internal | ST97 | Strategic | External Budget Book | Corporate Finance | Corporate Accounting | 2025-03-31 | [6 empty] | Publication of EP External Budget Book on Website

## Meeting Dates
Key Meeting Dates
Efficiency and Savings Board
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2024-03-12 | Share Budget Setting Timetable. | S1
2021-06-07 | Efficiency, Savings & Growth Board | 2024-07-09 | Initial Strategic discussion on savings proposals received to date from commands (decisions required on which ones to progress) | S6
2021-09-06 | Efficiency, Savings & Growth Board | 2024-09-12 | Overall savings proposals from commands prior to 7P Assessment agreed for inclusion in the next stage of the budget setting process. | S12,ST27
2021-11-22 | Efficiency, Savings & Growth Board | 2024-11-05 | Verbal budget update to Efficiency and Savings Board | ST53
Estates Change Board |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| Estates Change Board | 2024-07-22 | Estates capital bids or significant increases to existing bids (more than 10% or £50k change) | C3
2021-10-05 | Estates Change Board | 2022-10-24
Key Meeting Dates Cont.
Digital Transformation Oversight Board (DTOB) |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| DTOB | Jul/Aug (TBC) | Approval of IT Capital Bids or significant increases to existing bids to progress to SCCB | C4
Strategic Change & Co-ordination Board |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| SCCB | 2024-10-07 | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment. | IO8, S15, C8, ST36
COG Dates |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| COG | 2024-05-29 | MTFS Q1 presented to COG. | ST7
|  | 2024-06-12 | Briefing and progress update on Continuous Improvement Programme | ST14
|  | 2024-06-26 | MTFS Monthly Update | ST17
|  | 2024-07-24 | MTFS Monthly Update and decisions on investment bids to be progressed. | ST21
|  | 2024-08-21 | MTFS Monthly Update | ST23
2021-09-08 | COG | 2024-09-18 | Update of MTFS Q2 presented to COG with high level view of Investment and Savings. Would include latest position submitted for Efficiency and Savings Board on 12th September. | ST29
2021-10-20 | COG | 2024-10-16 | COG Budget Workshop (1 of 2) – review of provisional Capital & Revenue investment, savings and MTFS. Pay budgets not included. | ST41
2021-11-17 | COG | 2024-11-13 | COG Budget Workshop (2 of 2 inc. pay) – review of provisional Capital & Revenue investement, savings and MTFS. Includes pay and allocation of officer overtime budgets | ST56
2021-12-07 | COG | 2024-12-11 | COG review first draft of budget letter | ST63
| COG | 2024-12-23 | Virtual Review of Budget post HO Funding Announcement | ST75
2022-01-12 | COG | 2025-01-08 | COG: Final review of Chief Constable's budget proposal letter post HO funding announcement. (Virtual) - to include Appendicies with subjective summary | ST83
Strategic Board |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
2021-06-10 |  | 2024-03-05 | 2025/26 Draft Budget Setting Timetable and MTFS (Q4 based on Month 10 & Prior Year Budget Setting papes) presented to Strategic Board | ST2
2021-06-10 |  | 2024-06-10 | MTFS (Q1) & Updated Budget Setting Timetable presented to Strategic Board (based on reports presented to COG on 15th and 29th May). Draft paper to be circulated to PFCC Office 7th June. | ST12
|  | July (TBC) | Extraordinary Board to brief on Contiuous Improvement Programme | ST20
2021-09-27 |  | 2024-09-24 | MTFS (Q2) presented to Strategic Board (based on report presented to COG on 18th Sept). | ST33
2021-12-14 |  | 2024-12-19 | Strategic Board - Chief Constable presents Budget Proposals including Officer investment (Prior to HO Funding Announcement) | ST71
|  | March 2024 (TBC) | Approval of 2025/26 Budget (including POA Analysis) and MTFS including accompanying Decision Report | ST96
Chief Constable / PFCC Liaison Meetings |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2024-09-20 | Pre-meet for the Q2 MTFS position ahead of Strategic Board | ST31
2021-11-05 |  | 2024-10-25 | Meeting with PFCCs Office to review a précis of Capital & Revenue investment, savings and MTFS. Attended by DCC & CC. - Post COG Workshop | ST47
2021-11-24 |  | 2024-12-16 | PFCC & Chief Constable meeting to discuss latest budget setting position. | ST67
|  | 2024-12-20 | MTFS/Budget Setting Review post Home Office Funding Announcement (inc adherence to Police, Fire and Crime Plan) - Includes near final draft of Chief Constable's letter | ST74
2022-01-05 |  | 2024-01-06 | Chief Constable meets with PFCC to discuss Chief Constable's Budget letter | ST80
Police Fire & Crime Panel - Budget Working Group |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2024-10-10 | Budget Setting Working Group (1) | ST38
|  | 2024-11-05 | Budget Setting Working Group (2) | ST52
|  | 2025-01-07 | Budget Setting Working Group (3) | ST81
|  | 2025-01-14 | Budget Setting Working Group (4) | ST87
Police Fire & Crime Panel |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2024-07-25 | Presentation of Budget Setting Paper describing activities and process/timetable for budget setting | ST21
|  | 2024-10-03 | Police, Fire and Crime Panel | ST35
|  | 2024-12-05 | Police, Fire and Crime Panel | ST62
2022-02-03 |  | 2025-02-04 | PFCC presented budget to panel | ST89
|  | 2025-02-18 | PFCC presented budget to panel (reserve date) | ST92
,

## Corp Fin timetable (hidden)
Pay Budget Setting - Timetable - Corporate Accounting
Category of Activity | Activity | Responsible Team/Owner | Last Year's Deadline | Deadline
PCSO Costings | Blank PCSO PBS costings file for 2022/23 to be created ready for populating | CAT | 2021-08-27 | 2021-08-27
Costings | Blank PSE/Officer PBS costings file for 2022/23 to be created ready for populating. | TRA | 2021-08-27 | 2021-08-27
Costings | Sense check of costing files to ensure no historical links, comments etc. | HOCA | 2021-08-31 | 2021-08-31
Establishment | Initial download for PBS issued by Organisation Management (OM) | HR | 2021-09-01 | 2021-09-01
Establishment | Establishment tables issued to HRAs/Heads of Dept./Command | FBPs/MAs | 2021-09-08 | 2021-09-08
Establishment | Reminder to be sent with confirmation of deadline | FBPs/MAs | 2021-09-15 | 2021-09-15
Establishment | Deadline for the return of completed establishment tables | HRAs/Heads of Dept./Command | 2021-09-17 | 2021-09-17
Establishment | First weekly trackers to be received from OM team. To be sent each Friday until 8th October. | HR | 2021-09-17 | 2021-09-17
Establishment | Review establishments/changes and ensure HR to follow up before deadline of 8th October | FBPs/MAs | 2021-09-24 | 2021-09-24
Costings | PCSO costings file ready for review - HR download added, payroll checks finished (over £100) Allowances/Pension/NI Workings complete & summary table populated. | CAT | 2021-09-24 | 2021-09-24
Costings | Staff/Officers costings file ready for review. Establishment reflective of HR download/trackers, Allowances/Pension/NI/Increment calculations complete. Summary table populated. | TRA | 2021-09-24 | 2021-09-24
Costings | Agree format for Officer turnover calculations | HOCA/CA | 2021-09-30 | 2021-09-30
All | PBS Review | Corp Act | 2021-09-30 | 2021-09-30
Costings | To review staff/officer costings file for formula errors and large variances to previous years file. | HOCA | 2021-10-01 | 2021-10-01
Costings | To review PCSO costings file for formula errors and large variances to previous years file. | RTA | 2021-10-01 | 2021-10-01
Costings | Deadline for virements impacting on all pay codes - Month 6 MMR deadlines | All | 2021-10-04 | 2021-10-04
Costings | CFO review 1 of 2 | All | 2021-10-05 | 2021-10-05
Establishment | Deadline for last HR Tracker with approved changes. No further changes to be made without COG/Star Chamber approval. | All | 2021-10-08 | 2021-10-08
Costings | Ensure all tracked changes are included on costings files, with reconcilation to original download | RTA/CAT | 2021-10-11 | 2021-10-11
Costings | Circulate copy of costings for review by FBP&MA team | RTA | 2021-10-11 | 2021-10-11
Establishment | Reconciliation of Establishment and Holding Codes (i.e. growth included on PBS and outstanding, recurring budget requirement for growth) | FBP - Strategic Change/RTA | 2021-10-15 | 2021-10-15
Costings | FBP&MA to review costing files for cost centres/POA, funding source (i.e. Force vs External) | FBP/MAs | 2021-10-15 | 2021-10-15
Costings | COG budget workshop provisional review (1 of 2) (no pay budgets) | HOCA | 2021-10-20 | 2021-10-20
Costings | Prepare budget/calculate turnover. | HOCA | 2021-10-22 | 2021-10-22
Costings | To review all costings files. | ChA | 2021-10-27 | 2021-10-27
Costings | CFO review 2 of 2 | Corp Act | 2021-11-05 | 2021-11-05
Finalisation | COG budget workshop (2 of 2) to include Pay | CFO/ChA/Head of FBP & MA | 2021-11-17 | 2021-11-17
Finalisation | Verbal Budget update to Efficiency, Savings and Growth Board | CFO/ChA | 2021-11-22 | 2021-11-22
Costings | PBS files issued to CFO & DCC | HOCA | 2021-11-22 | 2021-11-22
Costings | Autumn Statement - NI | RTA | TBC | TBC
Finalisation | PFCC & Chief Constable - discuss latest budget proposals | Chief Constable (supported by CFO) | 2021-11-24 | 2021-11-24
Finalisation | COG: Review Chief Constable's Budget Proposal to PFCC (Post HO announcement) | CFO/ChA | 2021-12-07 | 2021-12-07
Finalisation | Strategic Board - Budget proposals & Investments | Strategic Change | 2021-12-09 | 2021-12-09
Finalisation | PFCC presents proposed budget at Police Fire and Crime Panel | Chief Constable (supported by CFO) | 2022-01-03 | 2022-01-03
Budget Preparation | Deadline for 2022/23 FYE Virements (non-pay) to Chief Acccountant for approval (via pending virements process) | All | 2021-11-01 | 2021-11-01
Budget Preparation | Send final confirmed establishments following tracked changes (no budgets) | FBPs/MAs | 2021-12-01 | 2021-12-01
Budget Preparation | Prepare 2022/23 Budget Build file, clear down prior pay budgets and ensure FYE included. | RTA | 2021-12-03 | 2021-12-03
Budget Preparation | Strategic Board budget review | Chief Constable (supported by CFO) | 2021-12-09 | 2021-12-09
Budget Preparation | Calculate pay allocations (to include averages for Officers & PCSOs) for review by MA(pay) | RTA | 2021-12-10 | 2021-12-10
Budget Preparation | Confirm outcome of COG: Review Chief Constable's Budget Proposal to PFCC (Post HO announcement) | CFO/ChA | 2021-12-10 | 2021-12-10
Budget Preparation | Send the growth & saving costing for coding to MAs/FBPs | ChA | 2021-12-10 | 2021-12-10
Budget Preparation | Return coded growth & savings | FBPs/MAs | 2021-12-17 | 2021-12-17
Budget Preparation | Populate budget build with pay allocations | RTA | 2021-12-17 | 2021-12-17
Budget Preparation | Populate budget build with growth & savings and issue model to MAs/FBPs for review. | RTA | 2021-12-20 | 2021-12-20
Pre upload | Build force growth into budget build | RTA/FBP Strategic Change | 2021-12-20 | 2021-12-20
Budget Preparation | Send Budget Build file for review | RTA | 2021-12-23 | 2021-12-23
Budget Preparation | Send any adjustments/changes to budget build to RTA (to include budget movements/POA changes) | FBPs/MAs | 2022-01-07 | 2022-01-07
Budget Preparation | Finalise budget build at subjective heading level - to include any FBP/MA changes | RTA | 2022-01-07 | 2022-01-07 | JS Amended from 14/1
Budget Preparation | Subjective summary of proposed budget to PFCC | ChA | 2022-01-07 | 2022-01-07 | JS Amended from 14/1
Budget Preparation | PFCC Panel approve budget |  | 2022-02-03 | 2022-02-03
Pre upload | Confirm final precept investment | ChA | 2022-02-09 | 2022-02-09
Pre upload | Confirm final budget agreed and any additional changes to Corporate Accounting | ChA | 2022-02-09 | 2022-02-09
Pre upload | Budget build file frozen | Corp Act | 2022-02-11 | 2022-02-11
Finalisation | 2022/23 budget uploaded into SAP | Corp Act | 2022-02-18 | 2022-02-18
Finalisation | 2022/23 Draft internal budget book created | Corp Act | 2022-02-18 | 2022-02-18
Finalisation | Distribure copy of 2022/23 internal budget book, report any mispostings back to Corporate Accounting - include review of SAP for completeness | FBPs/MAs | 2022-02-25 | 2022-02-25
Finalisation | Mispostings corrected on SAP and internal budget book updated. | Corp Act | 2022-02-28 | 2022-02-28
Finalisation | 1st Draft of External budget book sent to Chief Accountant for review | HOCA
Finalisation | To return external budget book with comments/feedback | ChA
Finalisation | 2nd draft external budget book sent to CFO for review. | Head of Corp Act
Finalisation | To return external budget book with comments/feedback | CFO
Finalisation | Load 2023/24 base budget (plan 2) on SAP | Corp Act | 2022-03-31 | 2022-03-31
Finalisation | 2021/22 Internal budget book and estabilshment tables (with budgets) sent to Budget Holders. | Corp Act

## Queries (hidden)
New Additions to the Timetable this year
Allocation of Overtime budgets to Chief Officers | To be taken to Budget Workshop 2
Allocation of COG contingency budgets | To be taken to Budget Workshop 2
Circulation of bids, growth etc sent to panel for budget holders | Added circulation date of 10th December
Circulation of internal budget book | Added end of Feb date
External Budget Book | Added end of March date
sending out establishment reports | Added to end of Feb date
revenue bid templates - confusion on who to complete - we changed the process for 21/22 budget setting. Need to be clear that command provide SME wording | Wording updted in timetable - BPs submit but with input from SMEs
Queries Outstanding
Add in a tab for PFCC timelines - last year needed to fit in around JAC pre-meets
explanation of timelines to Budget Holders in our comms to explain steps - budget holder comms strategy - not rely on feedback from boards
Build Build Timetable to be refreshed and ensure build in need for subjective summary for the Chief Constable's letter on (COG Final Review on 12th January 22) | PFCC wants POA analysis of budget but work on budget build commences after panel. Budget pulled together top down and detailed coding including POA is concluded after panel. If required at the same time as panel, resouces would need to be re-directed to Corporate Accounting from elsewhere within Corporate Finance or temporary additional resource identified.
load of budget - full year v part year - may cause problems next year | Sam to provide instructions
bigger picture of savings and growth at the time of decision making | Anna working on SCD as a pilot
change log at a particular point in time (2nd COG budget workshop) on business cases.
Richard raised issue of HR and the updating of base data for pay budget setting and delays from HR
Pay Budget Setting spreadsheet - controls - Matt
PUP Spreadsheet (controls on reasonable) - Amanda to add reasonable checks
Review of pay budget setting model - me
Allocation to cost centres earlier - timetable
Coding of bids - end of November hard stop to review what has gone to COG
Extraordinary SCCB Agenda - Anna / Annette Comms Strategy (Connexions and our intranet page)
Turnover to revamp - Matt / Tech Rev Accountant (in the Summer)
RBC - Instructions - need better comms. And instructions on Non-Pay - take to MMR Meeting
Budget Load proceedure - Sam and I
HRA Involvement - key date is still 31st August as take download 1st Sept. Meeting mid July with HRA/HRBPss and disseminate information for them to review